{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["List1","List2","List3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"List1","index":0,"n_rows":24,"n_cols":5,"rows_kept":24,"flags":["formulas_cached_only"]}
[]
["REKONSTRUKCE  CHODNÍKU  V  PŘÍBOŘE"]
[]
[null,null,"        ČASOVÝ HARMONOGRAM  PRACÍ"]
[]
["  MĚSÍC ( rok 2012  )","září","říjen","listopad","prosinec"]
[]
[]
[]
["        Název ulice"]
[]
["Ulice nadpor. Loma","   X","    X      X      X      X","    X      X      X      X"]
["Ulice Šafaříkova",null,"                     X      X             ","    X      X      X      X","    X      X      X      X"]
["Ulice 28. října","   X","    X      X      X      X","    X      X      X      X"]
["Ulice Pionýrů",null,"                    X      X             ","    X      X      X      X","   X      X      X     "]
[]
[]
[]
[]
[{"$nulls":4},"Zdeněk Jeníš"]
[{"$nulls":4},"jednatel společnosti"]
[{"$nulls":4},"JAPSTAV MORAVA s.r.o."]
[]
["V Kopřivnici  17.9. 2012"]

{"sheet":"List2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"List3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}